## Team Meeting 4
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Jolene | Aloysius | Jacob | Qian Yi | Samuel | Zeta
Team member's mood during the this week's meeting: |  |  | Excited | Neutral | Happy | Excited | Happy | Neutral
1 | Documentations | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 10 | 10 | 9 | 7.6667 | 7.8333 | 12.5 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Allocated by Team Leader | Yes | 12 | Neutral | 9.6667
| Estimated Task Priority（0-10） |  | 7 | 8 | 6 | 9 | 10 | 6
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 9 | 6 | 8 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 13 | 12 | 12 | 11 | 13 | 14
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 7 | 10 | 9 | 8
2 | Code Integration | Task Quality Evaluation (After Task Completed) | 9 | 9 | 10 | 9 | 9 | 10 | 9 | 8 | 3.1667 | Jolene | Jacob Zeta | Allocated by Team Leader | Yes | 2 | Excited | 9.3333
| Estimated Task Priority（0-10） |  | 9 | 10 | 10 | 8 | 7 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 6 | 9 | 10 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 1 | 4 | 5 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 10 | 8 | 7 | 10
3 | Testing | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 9 | 10 | 8.3333 | 8.6667 | 10.8333 | Jolene | Aloysius | Through Discussion | Yes | 11 | Excited | 9.5
| Estimated Task Priority（0-10） |  | 8 | 10 | 9 | 7 | 7 | 9
| Estimated Task Difficulty（0-10） |  | 10 | 7 | 8 | 10 | 9 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 12 | 9 | 10 | 13 | 11
| Team Member's Confidence about the Task (0-10) |  | 8 | 10 | 10 | 8 | 8 | 7
4 | Presentation Preparation | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 10 | 9 | 9 | 8.8333 | 7.1667 | 10.3333 | Jolene | Qian Yi Samuel | Through Discussion | Yes | 7 | Happy | 9.3333
| Estimated Task Priority（0-10） |  | 10 | 9 | 7 | 10 | 9 | 8
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 8 | 5 | 8 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 12 | 7 | 9 | 11 | 13
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 7 | 10 | 9 | 8