## Team Meeting 3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Jolene | Aloysius | Jacob | Qian Yi | Samuel | Zeta
Team member's mood during the this week's meeting: |  |  | Neutral | Happy | Sad | Neutral | Sad | Excited
1 | Project Plan + Risk Maanagement Plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 8 | 10 | 9 | 8 | 9.1667 | 7.4 | 6 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Allocated by Team Leader | Yes | 5 | Happy | 9.4
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 10 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 8 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 6 | 8 | 5 | 6 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 7 | 8 | 8 | 8
2 | Code Functions | Task Quality Evaluation (After Task Completed) | 8 | 9 | 9 | 8 | 7 | 10 | 9.3333 | 7.6 | 9.4 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Through Discussion | Yes | 8 | Excited | 8.2
| Estimated Task Priority（0-10） |  | 8 | 10 | 9 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 6 | 8 | 8 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 10 | 7 | 10 | 10 | 8
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 10 | 7 | 9 | 8
3 | Prototype Demo Preparation | Task Quality Evaluation (After Task Completed) | 7 | 8 | 10 | 9 | 8 | 9 | 8.3333 | 7.8 | 3.6 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Through Discussion | Yes | 2 | Neutral | 8.4
| Estimated Task Priority（0-10） |  | 7 | 8 | 9 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 8 | 8 | 8 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 4 | 3 | 4 | 7
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 8 | 7 | 7 | 8