## Team Meeting 1
| Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Jolene | Aloysius | Jacob | Qian Yi | Samuel | Zeta
Team member's mood during the this week's meeting: |  |  | Happy | Neutral | Neutral | Happy | Neutral | Excited
1 | Deciding of team name & member roles | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 7.8333 | 3.3333 | 1 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Through Discussion | Yes | 1 | Excited | 10
| Estimated Task Priority（0-10） |  | 7 | 8 | 8 | 8 | 8 | 8
| Estimated Task Difficulty（0-10） |  | 3 | 1 | 1 | 5 | 4 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 10 | 8 | 8 | 10
2 | Deciding of project topic & functions | Task Quality Evaluation (After Task Completed) | 10 | 9 | 8 | 10 | 10 | 10 | 10 | 7.3333 | 2 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Through Discussion | Yes | 1 | Excited | 9.5
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 9 | 9 | 8 | 6 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 2 | 1 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 7 | 8 | 7 | 7
3 | Writing of project proposal | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 | 9 | 9 | 10 | 9.8333 | 7 | 2.5 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Allocated by Team Leader | Yes | 5 | Happy | 8.8333
| Estimated Task Priority（0-10） |  | 9 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 10 | 9 | 5 | 7 | 5 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 2 | 2 | 2 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 7 | 7 | 8 | 8 | 9 | 9