## Team Meeting 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Jolene | Aloysius | Jacob | Qian Yi | Samuel | Zeta
Team member's mood during the this week's meeting: |  |  | Happy | Neutral | Neutral | Neutral | Happy | Happy
1 | Analysis Models | Task Quality Evaluation (After Task Completed) | 8 | 8 | 7 | 8 | 8 | 8 | 9.8333 | 6.5 | 3.8333 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Allocated by Team Leader | Yes | 2 | Happy | 7.8333
| Estimated Task Priority（0-10） |  | 10 | 9 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 6 | 7 | 8 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 4 | 5 | 4 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 9 | 7 | 8 | 8
2 | SRS & Quality Plan | Task Quality Evaluation (After Task Completed) | 7 | 7 | 7 | 8 | 8 | 8 | 9.6667 | 8.1667 | 10.3333 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Through Discussion | Yes | 4 | Happy | 7.5
| Estimated Task Priority（0-10） |  | 9 | 10 | 10 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 9 | 10 | 6 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 12 | 10 | 10 | 10 | 10
| Team Member's Confidence about the Task (0-10) |  | 9 | 7 | 8 | 9 | 7 | 8
3 | UI Mockup | Task Quality Evaluation (After Task Completed) | 6 | 7 | 7 | 8 | 7 | 7 | 7.8333 | 5.6667 | 3.1667 | Jolene | Qian Yi Zeta | Through Discussion | Yes | 2 | Excited | 7
| Estimated Task Priority（0-10） |  | 6 | 7 | 9 | 8 | 9 | 8
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 6 | 6 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 4 | 3 | 4 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Code Functions | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 8 | 8 | 8 | 6.8333 | 8.5 | 13 | Jolene | Aloysius Jacob Qian Yi Samuel Zeta | Through Discussion | Yes | 7 | Happy | 8
| Estimated Task Priority（0-10） |  | 5 | 7 | 8 | 7 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 7 | 9 | 10 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 11 | 13 | 12 | 14 | 14 | 14
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 9 | 7 | 7 | 7